## Hoja 1
Risk / Opportunity | Probability | Qualitative Impact | Consequence / Issue | Quantification Assumption | Cost Driver | Estimated Impact (€) | Expected Value (€)
Data Quality / KPIs | 80% | High | Without a standardized data quality framework, additional effort may be required for data validation, mapping and correction activities. | X additional hours for validation/correction | Additional validation/correction hours × hourly rate | To be estimated | 80% × Impact €
Scalability & Deliverables | 70% | High | Lack of standardization and automation may increase the effort required for future data transformations and deliverables, limiting scalability. | X hours/delivery × X expected deliveries | Additional transformation effort per delivery × expected nº of deliveries | To be estimated | 70% × Impact €
Responsibilities, Roles & Integration Limits | 40% | Medium | Unclear responsibilities and integration boundaries may generate additional coordination, clarification and rework, potentially impacting the schedule. | X additional coordination/rework hours | Additional project effort caused by coordination/rework | To be estimated | 40% × Impact €
Dummy Data Procedures & Management | 40% | Medium | Absence of a standardized dummy-data process may increase transformation and validation complexity and require additional manual activities. | X additional transformation/validation hours | Additional transformation/validation hours × hourly rate | To be estimated | 40% × Impact €
Stakeholder Communication Management | 80% | High | Insufficient communication and alignment may lead to late requirement clarification, rework and schedule delays. | X rework hours + X coordination hours | Rework hours + additional coordination effort + potential delay cost | To be estimated | 80% × Impact €
Impact → evaluación cualitativa actual.
**Data Quality / KPI opportunity**
Failure to implement the proposed data quality KPI framework may result in increased manual effort for data validation and mapping activities, potentially requiring additional resources and increasing the overall delivery cost.
**Scalability / Automation opportunity**
If the proposed solution is not implemented, future data transformations may require additional manual effort and more complex processing activities, limiting scalability and potentially increasing recurring delivery costs.
**Responsibilities, Roles & Integration Limits**
Unclear responsibilities and integration boundaries may lead to additional coordination effort, rework and schedule delays. This may result in approximately one additional month of project effort, depending on the level of clarification required.
**Dummy Data Procedures & Management**
Failure to establish an appropriate dummy-data process may increase the complexity of data transformation and validation activities, resulting in additional manual effort and reduced automation efficiency.
**Stakeholder Communication Management**
Insufficient stakeholder communication and alignment may lead to late clarification of requirements, rework and potential delays. In a worst-case scenario, this could require additional project effort and affect the planned delivery schedule.
Consequence ¦ Cost Driver ¦ Estimated Impact (€) ¦ Risk Exposure (€)
Cost Driver: 1 additional month × affected resources × monthly rate
risk exposure = % * cost driver
beneficio/ahorro esperado (probabilidad × ahorro potencial); en riesgos, cost exposure (probabilidad × coste potencial).